## Sheet1
TASK | TASK Descr / Detail | Person(s) working it | Completion
Decide on project topic | Pets, Baseball, real estate. RE it is. | all | 100%
Find / decide on APIs, CSVs, datasets to use | Zillow, ATTOM, Google places | all | 100%
Write up & submit proposal | See PPT from Jeff for outline | Tim | 100%
Gather School Data
Gather zip codes | Get 30 or so. St Louis areas. Manual is fine, put in CSV? | Brandon | 100%
Get lat & lng for the zip codes | Use API if possible?? Or do manually using a conversion site | Sammi, David, Tim | 100%
Use ATTOM - schoold districts info to get school a school disctric for each zip | May have to do manually by looking at JSON data on ATTOM site, since there are multiple districts per zip. Use public school. Set radius to 3 miles?? Important data to get is OBInstID for the high school. See Data\school_zip_lat_long.csv for info and to fill in. See Misc\How_to_get_OBInstID.rtf for detailed instructions. Put into csv file. | Sammi, David | 100%
Use OBInstID from ATTOM general school search above, in API calls to get school detail | Read csv. Use API. Parse JSON. Put into Pandas data frame. | Tim | 100%
Use (high) SCHOOL detail? Or DISTRICT detail? | Go with School - high school if possible, middle if not avail for zip | All | 100%
If District, we need Obdistrictnumber from school detail records to use for districtdetail API | N/A - going with School info
Gather Real Estate Data
Decide what real estate data to gather (in conjunction with school info above) |  | All | 100%
Use ATTOM - Propert extended to get GeoID for each lan & long (zip) used for schools above | Use Property Extended: /property/snapshot with lat, lon again (like school) to get GeoID. Add to csv spreadsheet. | Brandon | 100%
Use GeoID in ATTOM Sales Trend by Year API | Use /salestrend/snapshot API. Pull 5 years - 2014 - 2018. Parse JSON. Put into Pandas data frame | Tim | 90%
Decide on a statistical model to use
Do it / write code / calculate it
Create graphs |  | David & Sammi
Do it/ write code/ create & save png
Development requirements:
Use Pandas to clean and format your dataset(s).
Create a Jupyter Notebook describing the data exploration and cleanup process.
Create a Jupyter Notebook illustrating the ﬁnal data analysis.
Use Matplotlib to create a total of 6–8 visualizations of your data (ideally, at least 2 per ”question” you ask of your data).
Save PNG images of your visualizations to distribute to the class and instructional team, and for inclusion in your presentation.
(Optional) Use at least one API, if you can ﬁnd an API with data pertinent to your primary research questions. | Used Google API for zip to lat, lon. Used multiple ATTOM APIs for School data and real estate data |  | 100%
Create a write-up summarizing your major ﬁndings. This should include a heading for each “question” you asked of your data and a short description of your ﬁndings and any relevant plots.
Prepare presentation | Use Google charts(??) or PowerPoint. Needs to be 10 minutes long.
Practice the presentation
Presentation requirements:
Questions you found interesting and what motivated you to answer them
Where and how you found the data you used to answer these questions
The data exploration and cleanup process (accompanied by your Jupyter Notebook)
The analysis process (accompanied by your Jupyter Notebook)
Your conclusions, which should include a numerical summary and visualizations of that summary
The implications of your findings: what do your findings mean?